## Workplan
Community Engagement Group Work Plan 2022
Community Engagement Group Work plan April 2022 - 2024 This has been created in conjunction with our CEG members (To be finalised at CEG meeting 28th April 2022)
Patient and Public Involvement Strategy 2022-2024
Community Engagement Work Plan
Objective | PPI Strategy aim | Portfolio / working groups |  | Activities | Expected Outcome | Progress | CEG lead | Members | Supported by… | Date to achieve | Complete
Ethos | We will engage with people compassionately giving honest information about the Trust. Using our patient’s voices to support improvements. | EEAST to share local and regional information |  | Local operational information mechanism of sharing to be developed to ensure CEG volunteers are better informed on EEAST matters, feel more involved and up to date. | CEG volunteers are better informed… | Monthly volunteer Q&A sessions started March 22, NTK sent out weekly. A monthly CEG communication email to be sent out to group updating them on progress against the workplan and other matter to commence end of October 2022. | CEG Chair, and CEG ICS co-ordinators |  |  | 2023-04-01
|  | Strategic matters |  | Agreement of membership of strategic meetings. Attend and contribute to the activities of the groups from the perspective of patients and the public, complying with the group terms of reference Providing direct input into Trust committees and work groups by representation. | All committee/work group outcomes appropriately reflect the views of patients and the public. CEG to receive reports from each delegate | PSEG, Safeguarding, E&D, IPC already identified, QGC, Trust Board, RIG, VAF attended by nominated CEG members | CEG Chair, Victoria Boyce, Gillian Langley |  |  | 2022-12-01
|  | Operational Matters |  | Agreement of membership of operational meetings. Attend and contribute to the activities of the groups from the perspective of patients and the public, complying with the group terms of reference Providing direct input into Trust committees and work groups by representation. | All committee/work group outcomes appropriately reflect the views of patients and the public. CEG to receive reports from each delegate | Meetings to be identified by HOOs. | CEG Chair, Victoria Boyce, Gillian Langley |  |  | 2023-04-01
|  | Complaints review panel |  | Members to attend and contribute to complaints review panels and SI panels as appropriate. | The process is reviewed continuously and is fair | Complaint reviews were taking place but put on hold due to recruitment in PE team in December 21. New substantive PE manager now in post (Mar 22) Complaints review training meeting held 13/10/22, bi-monthly complaints response packs to be sent to CEG members involved to review. Twice a year face-to-face get togethers to be planned. | Kathryn Kerr / Gillian Langley |  |  | 2022-12-01
Each case is conducted fairly in accordance with the best practice process
|  | Discovery interviews |  | Undertake training in the discovery interview technique and recording of interviews. | CEG volunteers are competent and confident to conduct patient discovery interviews, increasing support for the PPI team. | Discovery interview process continuing. New equipment purchased to enable more interviews to take place. Small group of CEG members have taken part in first training session held 29/09/2022, follow up scheduled for… Patient Experience Management Team training session also held on 11/10/22. Discovery interviews involving CEG members to commence Nov 2022. | PPI team |  |  | 2023-04-01
|  |  |  | Support the PPI team with arranging and interviewing patients responding through patient surveys who would like to take part in a discovery interview | CEG members are able to contact patients and conduct preliminary conversations about patient experience, and assist in organising full patient interviews as required.
|  |  |  | Support the PPI team with future live patient discovery interview processes | TBC if live interviews are to be adopted by the Board.
|  | Reader panel |  | Review documents produced by EEAST to provide a patient and public perspective, a sense check on understanding and language used. | All forms of Trust communications are accessible and meet the needs of the intended recipients | Patient Safety Improvement Specialist has been trained in accessability and now has access to social media accounts. Comms to be involved in discussions with CEG members to agree clear plan. | PPI team and Communications team |  |  | 2023-08-01
Involvement and Engagement | The Trust will plan and work with our staff and volunteers to offer a greater variety of engagement & involvement opportunities. | Community Engagement |  | Presentations and talks to community groups. Through presentations CEG members will assist the public to use their ambulance service appropriately and effectively, care for themselves to minimise the need for emergency calls, prepare themselves and their home if they have to call. Promote the service and manage public expectations | Increased public knowledge of the ambulance service, how to use the service appropriately leading to reduction in inappropriate use of the service. Reduced number of complaints. | IPC Risk assessment Developed with checklist to share with anyone undertaking engagement activities. Due to recommence shortly (April 22) Community presentation shared with PPI team and ICS Coordinators for use with groups in Norfolk. CEG to coproduce an updated presentation for use with community groups and for school and educational visits. School and Education visits have taken place in December 21 to March 22. | Speciality portfolio holders, ICS Leads and CEG Chair. |  |  | Development of presentations - August 2022. Stronger links with community groups April 23
|  |  |  | Develop links with community groups | Improved knowledge of the ambulance service in the communities EEAST serves. Improved engagement and understand of the experience and issues of different communities.
|  |  |  | School and educational visits | Improved knowledge of the ambulance service, basic life support, how to call 999, and the role of a paramedic amongst school children. Increased interest in the ambulance service as a future career option. Fears and barriers broken down.
|  | Events |  | Members to assist with finding community engagement events and opportunities in their ICS area. Members can help co-ordinate attendence at events to represent EEAST with agreement and support from the PPI team. This may include setting up stalls, and liasing with PPI team to provide resources. . Through events CEG members will assist the public to use their ambulance service appropriately and effectively Promote the service and manage public expectations | Increased public knowledge of the ambulance service, how to use the service appropriately leading to reduction in inappropriate use of the service. Reduced number of complaints. | Norfolk CEG members hosting a stall at Morrisons in Cromer once a month, also co-ordinating with the Norfolk CFR team. This is to be shared with the ICS Coordinators to replicate approach. CEG member attending Golden Age Fayres in Cambridgeshire working with Fenland Council and event attended Festival for older people in Flitwick. | All CEG Members |  |  | 2024-03-01
|  | IPC |  | Ensure a representative of the CEG attends all IPC meetings | CEG better informed about IPC issues / developments at EEAST. The patient and public voice is represented and reflected in the work of the IPC group. | CEG member appointed to IPC meetings (Alan J and Alan S) | Alan Jackson |  |  | Ongoing
|  |  |  | CEG members to take part in vehicle and station IPC audits when covid restrictions allow to give the lay person perspective on IPC compliance on trust premises and vehicles. Contribute to the periodic IPC reports made by the Trust IPC lead. Make appropriate ad hoc IPC inspections Outcomes to be included in reports to the Board | Contribute to the periodic IPC reports made by the Trust IPC lead. Make appropriate ad hoc IPC inspections. Outcomes to be included in reports to the Board.
|  | Research |  | Members to be involved and activitely participate in trust led research projects as and when they arise. | Representation of the patient and public voice included in research projects. | SG taking part in the cessation study. Members involved in the Research Involvement Group | TBC |  |  | 2024-03-01
|  | Staff training |  | Support the EEAST training and education team where possible. Engage with staff at appropriate opportunities to provide public and patient views | CEG members specialist skills are utilised appropriately. | Request to assist a member of staff with an assignment for their Elizabeth Garrett Anderson course. Acting as patient rep (April-May 22). CEG member and Patient Experience Lead have drafted a compassion and empathy Course for front line staff. Delayed due to face-to-face nature and IPC. PPI team to investigate how CEG can be involved in staff induction delivery (Oct 2022) | Indra Jones |  |  | 2024-03-01
[5 empty] | Increased engagement with staff to enhance their understanding of patient and public expectations. |  | TBC |  |  | 2023-08-01
|  | Specialist portfolios for engagement/ involvement | Leads to be identified and linked in with relevant clinical lead and specialist community groups.
|  |  | Women and children | Co-production of activities with clinical lead TBC | To increase engagement with Patient Representatives and Clinical Leads. Able to support with specialist projects. | CEG members have expressed their interest in supporting specialist portfolios see members. Single lead to be agreed for each group. | Madeleine Donohue |  |  | 2023-04-01
|  |  | Mental health | Co-production of activities with clinical lead TBC | To increase engagement with Patient Representatives and Clinical Leads. Able to support with specialist projects. | CEG members have expressed their interest in supporting specialist portfolios see members. Single lead to be agreed for each group. |  |  |  | 2023-04-01
|  |  | End of life | Co-production of activities with clinical lead TBC | To increase engagement with Patient Representatives and Clinical Leads. Able to support with specialist projects. | CEG members have expressed their interest in supporting specialist portfolios see members. Single lead to be agreed for each group. |  |  |  | 2023-04-01
|  |  | Trauma and critical care | Co-production of activities with clinical lead TBC | To increase engagement with Patient Representatives and Clinical Leads. Able to support with specialist projects. | CEG members have expressed their interest in supporting specialist portfolios see members. Single lead to be agreed for each group. |  |  |  | 2023-04-01
|  |  | Older people | Co-production of activities with clinical lead TBC | To increase engagement with Patient Representatives and Clinical Leads. Able to support with specialist projects. | CEG members have expressed their interest in supporting specialist portfolios see members. Single lead to be agreed for each group. |  |  |  | 2023-04-01
|  |  | LGBTQIA+ | Importance of this specialist portfolio is recognised but currently no members of the group are able to lead on this. Aim to recruit members to support this portfolio
|  |  | Young people | Co-production of activities with clinical lead TBC | To increase engagement with Patient Representatives and Clinical Leads. Able to support with specialist projects. | CEG members have expressed their interest in supporting specialist portfolios see members. Single lead to be agreed for each group. |  |  |  | 2023-04-01
|  |  | Disability and accessability | Co-production of activities with clinical lead TBC | To increase engagement with Patient Representatives and Clinical Leads. Able to support with specialist projects. | CEG members have expressed their interest in supporting specialist portfolios see members. Single lead to be agreed for each group. |  |  |  | 2023-04-01
|  |  | BAME | Importance of this specialist portfolio is recognised but currently no members of the group are able to lead on this. Aim to recruit members to support this portfolio
|  |  | Homelessness | Importance of this specialist portfolio is recognised but currently no members of the group are able to lead on this. Aim to recruit members to support this portfolio
|  |  | family and unpaid carers | Co-production of activities with clinical lead TBC | To increase engagement with Patient Representatives and Clinical Leads. Able to support with specialist projects. | CEG members have expressed their interest in supporting specialist portfolios see members. Single lead to be agreed for each group. |  |  |  | 2023-04-01
|  |  | Veterans | Co-production of activities with clinical lead TBC | To increase engagement with Patient Representatives and Clinical Leads. Able to support with specialist projects. | CEG members have expressed their interest in supporting specialist portfolios see members. Single lead to be agreed for each group. |  |  |  | 2023-04-01
Accessibility | The trust will review and implement new ways to engage with people in an accessible way. | Accessibility and linking with specialist groups |  | Make links and work with specialist groups in our region, engaging with them on a regular basis. | Improved engagement with specialist groups leading to improved understanding and awareness of needs and experiences of EEAST for the communities these specialist groups represent. | PPI Team have established relationships with SUN Network, PAN Disability Network and Local Healthwatch partners. Further groups to be identified and relationships built. Patient Safety Improvement Specialist has been trained on accessability via Comms. Patient Surveys Team will be supporting. PPI and Patient survey team meeting with NANSA to co-produce an Easy Read survey. | TBC
Networking | We will work with our teams, staff and volunteers to engage with a wider range of patient groups, representative and organisations. | Working with healthcare patient and public representative groups |  | Co-ordinate working with Healthwatch across the region, Citizens Senate, PPGs and other patient and public representative groups to ensure we have representation and hear feedback from as wide a range of groups as possible | Improved connections and engagement with healthcare representative groups, shared experiences and information. Better informed groups. | PPI currently attending Helathwatch meetings in Cambs and Peterborough. Contact to be made with other Healthwatchs and CEG members nominated to attend meetings where appropriate. Zsara from Citizens Senate attends CEG meetings to maintain links with EEAST and to represent the Senate. | Speciality portfolio holders, ICS Leads and CEG Chair.
|  | Recruitment Staff |  | Involvement in recruiting EEAST staff, assisting with recruitment and careers fairs and promoting careers at EEAST within local communities and through networks | Increased staff recruitment, and targets met, and interest in careers with EEAST. | CEG involvement in face-to-face recruitment events currently on hold awaiting risk assessment
|  | Recruitment CEG |  | Support the recruiting of new CEG members, covering all strands of diversity and being representative of the communities served by EEAST. | Increased CEG membership across the EEAST region, especially in areas where membership is currently low. | AJ contacted local Lions clubs and asked them to advertise joining the CEG. Norfolk CEG members promoting membership of the CEG at events in Cromer. | Alan Jackson, Victoria Boyce |  |  | 2023-03-01
[5 empty] | Increased diversity of membership, with new members recruited to represent communities and groups not currently engaged with EEAST or represented in the CEG. | Recruitment work to begin after 28th April |  |  |  | 2023-03-01
|  | CFR projects |  | TBC with active CFR CEG members, and CFR management where appropriate. | To be agreed by CFR group once it commences. | Group to plan first meeting after 28th April | Victoria Boyce/ Lorna Hayes |  |  | TBC
Communication | We will use the ideas gained during coproduction to develop a multimedia approach to sharing and promoting involvement and engagement. | ICS Co-ordinators |  | To facilitate and assist the Trust in addressing specific locality issues working on engagement activities as requested by local trust management or identified through CEG engagement | CEG members engaged with local ICS and EEAST ICS manager, aware of local issues. | CEG ICS leads identified. | Alan Jackson, Victoria Boyce |  |  | 2024-03-01